## Tabelle1
portfolio | LV1871-Many-teams-many-projects-team3extracted
INPUT
Restriction must-have | 80%
Restriction product | 100%
teams | Team3
month | capacity
2016-04-01 | 15
2016-05-01 | 15
2016-06-01 | 15
2016-07-01 | 10.5
2016-08-01 | 7.5
2016-09-01 | 15
2016-10-01 | 10.5
2016-11-01 | 7.5
2016-12-01 | 15
2017-01-01 | 15
2017-02-01 | 15
2017-03-01 | 15
2017-04-01 | 15
2017-05-01 | 15
2017-06-01 | 15
2017-07-01 | 15
2017-08-01 | 15
2017-09-01 | 15
2017-10-01 | 15
2017-11-01 | 15
2017-12-01 | 15
2018-01-01 | 15
2018-02-01 | 15
2018-03-01 | 15
projects |  | Project1 | Project2 | Project3 | Project4 | Project5 | Project6 | Project7 | Project8 | Project9 | Project10 | Project11 | Project12
type |  | must-have | must-have | must-have | must-have | product | product | product | product | strategic | strategic | strategic | strategic
priority |  | 0 | 0 | 0 | 0 | 20 | 22 | 24 | 26 | 30 | 32 | 34 | 36
deadline (last month) |  | 2016-12-01 | 2016-10-01 | 2017-08-01 | 2017-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | none | none | none | none
effort | Team3 | 27 | 18 | 18 | 19 | 17 | 26 | 24 | 28 | 19 | 23 | 15 | 28
OUTPUT
| Project1 | Project2 | Project3 | Project4 | Project5 | Project6 | Project7 | Project8 | Project9 | Project10 | Project11 | Project12
month | Team3 | Team3 | Team3 | Team3 | Team3 | Team3 | Team3 | Team3 | Team3 | Team3 | Team3 | Team3
2016-04-01 | 2.95 | 2.95 | 0 | 0 | 0.25 | 2.95 | 2.95 | 2.95 | 0 | 0 | 0 | 0
2016-05-01 | 2.5 | 2.5 | 0 | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0 | 0 | 0
2016-06-01 | 2.5 | 2.5 | 0 | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0 | 0 | 0
2016-07-01 | 1.75 | 1.75 | 0 | 0 | 1.75 | 1.75 | 1.75 | 1.75 | 0 | 0 | 0 | 0
2016-08-01 | 1.25 | 1.25 | 0 | 0 | 1.25 | 1.25 | 1.25 | 1.25 | 0 | 0 | 0 | 0
2016-09-01 | 2.5 | 2.5 | 0 | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0 | 0 | 0
2016-10-01 | 1.75 | 1.75 | 0 | 0 | 1.75 | 1.75 | 1.75 | 1.75 | 0 | 0 | 0 | 0
2016-11-01 | 1.5 | 1.5 | 0 | 0 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0
2016-12-01 | 3 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
2017-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0
2017-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 11 | 0 | 0
2017-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3 | 0
2017-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3
2017-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
2017-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
2017-07-01 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-08-01 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-11-01 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-12-01 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overflow | Team1
29
projects |  | Project1 | Project2 | Project3 | Project4 | Project5 | Project6 | Project7 | Project8 | Project9 | Project10 | Project11 | Project12
deadline (last month) |  | 2016-12-01 | 2016-10-01 | 2017-08-01 | 2017-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-06-01